## Feuil1
2021
Tasks | December |  |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  |  | May
| s1 | s2 | S3 | S4 | s5 | s1 | s2 | S3 | S4 | s5 | s1 | s2 | s3 | s4 | s1 | s2 | s3 | s4 | s5 | s1 | s2 | s3 | s4 | s5 | s1 | s2 | S3 | s4
Time manager deployement (test on a sample) | bar: January s1 to January S4
Tablets deployement (test on a sample) | bar: January s1 to January S4
Time manager deployement (all employers) | bar: January s5 to February s3
Tablets deployement (all employers) | bar: January s5 to February s3
Monthly report, first occurence | bar: February s4
Incident reporting application deployement | bar: February s4 to March s1
GPS trackers deployement (test on a sample) | bar: February s4 to March s4
Connected trash cans delivery (test on a district) | bar: March s2 to April s1
GPS trackers deployement (all trucks) | bar: March s5 to April s4
Connected trash cans delivery (all city) | bar: April s2 to May s2
Drones deployement | bar: April s2 to April s5
2021
Events | December s1: December; January s1: January; February s1: February; March s1: March; April s1: April; May s1: May
| s1 | s2 | S3 | S4 | s5 | s1 | s2 | S3 | S4 | s5 | s1 | s2 | s3 | s4 | s1 | s2 | s3 | s4 | s5 | s1 | s2 | s3 | s4 | s5 | s1 | s2 | S3 | s4
send mail to managers | bar: December s1
meetings with managers | bar: December s2 to December S3
send mail to employees | bar: December S4
meetings with employees | bar: December s5 to January s1
send letter to citizens | bar: January s2
Flyers | bar: January s2
speech to citizens | bar: January S3
Keynote | bar: January S4 to February s2
satisfaction's survey | bar: April s5 to May s1